## Backlog
Task ID | Epic | User Story | Assigned To | Story Points | Status | Priority
1 | Project Setup | Initialize project structure and GitHub repo | Simarjeet Kaur | 3 | To Do | High
2 | Project Setup | Create Flask app and basic routing | Sachin | 3 | To Do | High
3 | ML Model | Train plant disease detection model | Himanshu | 8 | To Do | High
4 | ML Model | Integrate model with Flask backend | Himanshu | 5 | To Do | High
5 | Frontend | Design homepage UI | Shyog | 5 | To Do | Medium
6 | Frontend | Implement image upload & preview | Shyog | 5 | To Do | High
7 | UI/UX | Improve styling and responsiveness | Umesh | 5 | To Do | Medium
8 | Features | Add multi-language support | Anshika | 5 | To Do | Medium
9 | Features | Add audio output feature | Sachin | 5 | To Do | Medium
10 | Testing | Test model accuracy and UI flow | Prathik | 3 | To Do | High
11 | Deployment | Deploy project on Hugging Face | Vikas | 3 | To Do | High
12 | Deployment | Deploy project on Render | Vikas | 3 | To Do | Medium